STATEMENT OF WORK

MediBook — Patient Portal & Clinic Management System

Prepared for: Apex Health Group Pvt. Ltd., Hyderabad

Prepared by: Stackular Technologies Pvt. Ltd., Hyderabad

Document version: 1.2

Effective date: 15 January 2026

Contract ref: STK-2026-AHG-001

1. Project Overview

Apex Health Group Pvt. Ltd. (“Client”) operates a chain of five private multi-specialty clinics across Hyderabad. The Client seeks to develop a unified digital platform — referred to herein as MediBook — to streamline patient appointment scheduling, clinical record access, and administrative operations across all clinic locations.

Stackular Technologies Pvt. Ltd. (“Vendor”) shall design, develop, test, and deploy this platform in accordance with the requirements specified in this SOW and the accompanying Business Requirements Document (ref: AHG-BRD-2026-01).

1.1 Objectives

- Reduce patient no-shows by enabling online booking and automated WhatsApp and SMS reminders

- Give doctors a unified, remotely-accessible view of patient histories across all clinic branches

- Eliminate manual billing errors by digitising invoice generation and online payment collection

- Provide clinic administrators with real-time operational dashboards across all branches

- Build a platform capable of accommodating additional clinic branches in the future

2. Scope of Work

2.1 In-scope deliverables

- Responsive web-based patient portal accessible via desktop and mobile browsers

- Native mobile application for Android and iOS platforms

- Doctor-facing web dashboard for schedule management and patient record access

- Admin panel for clinic configuration, staff management, billing, and reporting

- Backend API services, database, and cloud infrastructure setup and deployment

- Integration with the Client's existing billing system (Tally ERP) and EMR system (Medi-Plus v3.2)

- Automated appointment notifications via SMS and WhatsApp

- User acceptance testing (UAT) support and production deployment

- 30 days of post-launch hypercare support

2.2 Out of scope

- Video or telemedicine consultation features

- Development of a new EMR system (integration with Medi-Plus v3.2 only)

- Hardware procurement (tablets, kiosks, reception hardware)

- Ongoing maintenance beyond the 30-day hypercare period (separate MSA required)

- Patient referral tracking module (noted as future requirement; not in scope for this engagement)

3. Deliverables and Timeline

The project is structured in four phases over sixteen weeks. Estimated production go-live: 9 May 2026. The timeline assumes the Client provides API access to the EMR and billing systems no later than 10 February 2026.

| Phase | Deliverable | Duration | Target Date |
| --- | --- | --- | --- |
| Phase 1 | Requirements confirmation, approved UI/UX wireframes, architecture document | 3 weeks | 5 Feb 2026 |
| Phase 2 | Patient portal, appointment booking, doctor dashboard (MVP) | 5 weeks | 12 Mar 2026 |
| Phase 3 | Admin panel, billing integration, EMR integration, notifications | 5 weeks | 16 Apr 2026 |
| Phase 4 | UAT, performance testing, bug fixes, production deployment | 3 weeks | 9 May 2026 |

Note: Delays in provision of API access or UAT sign-offs by the Client may impact the delivery schedule. Revised timelines will be agreed in writing.

4. Commercial Terms

4.1 Project value

Total fixed-price engagement value: INR 48,00,000 (Forty-Eight Lakhs Rupees), exclusive of applicable GST at 18%. Any changes to agreed scope will be governed by a formal Change Request (CR) process with separate cost and timeline implications.

4.2 Payment schedule

| Milestone | Trigger event | Amount (INR excl. GST) |
| --- | --- | --- |
| Advance | Contract signing | 14,40,000 (30%) |
| Mid-point | Phase 2 sign-off (MVP delivery) | 14,40,000 (30%) |
| Final | Phase 4 sign-off (production go-live) | 19,20,000 (40%) |

5. Assumptions and Client Obligations

- The Client will designate a primary project owner with authority to approve deliverables within 3 business days of submission.

- The Client will provide API or database credentials for Medi-Plus v3.2 and Tally ERP by 10 February 2026.

- The Client is responsible for all regulatory and legal compliance obligations relating to patient health data under applicable Indian laws.

- The Client will provide a full list and format of patient records to be migrated by 28 February 2026.

- UAT feedback will be submitted within 5 business days of each milestone delivery.

6. Acceptance Criteria

A milestone shall be considered accepted when:

- All functional requirements in the approved BRD for that phase are implemented and demonstrated.

- No Critical or High severity defects remain open at the time of sign-off.

- The Client's designated approver has signed the Phase Completion Certificate within the UAT window.

This Statement of Work is subject to the Master Services Agreement between the parties. In case of conflict, MSA terms shall prevail.

Authorised signatory — Client: Dr. Priya Nair, CEO, Apex Health Group Pvt. Ltd.

Authorised signatory — Vendor: Arjun Kapoor, Director, Stackular Technologies Pvt. Ltd.

Signature date: ________________________________