# PROJECT CHARTER

## CareFlow — Patient & Telehealth Management Platform

| Project Name | CareFlow |
| --- | --- |
| Project Sponsor | Dr. Rajiv Patel, CTO — MediConnect |
| Project Manager | Sarah Chen, VP Engineering — MediConnect |
| Vendor PM | Priya Sharma, Delivery Lead — Stackular Technologies |
| Charter Date | June 5, 2026 |
| Target Launch | January 15, 2027 |
| Budget | USD $1,850,000 |
| Document ID | PC-MC-2026-001 |

## 1. Project Purpose & Justification

CareFlow is initiated to eliminate MediConnect's reliance on three disconnected legacy systems, reduce administrative overhead by 40%, cut no-show rates by more than half, and achieve zero HIPAA audit findings by Q1 2027. The project addresses a $2.3M annual revenue leakage from no-shows and a $45,000 Q1 2026 HIPAA fine.

## 2. Project Objectives

Deliver a production-ready, HIPAA-compliant platform by January 15, 2027.

Achieve >=90% patient portal adoption within 90 days of launch.

Reduce no-show rate to <=10% within 6 months.

Reduce admin overhead per provider per day by >=40% within 6 months.

Pass third-party HIPAA penetration test with zero critical findings.

## 3. High-Level Scope

In Scope: Patient portal, provider dashboard, telehealth module, reminder engine, admin portal, iOS/Android apps, data migration, staff training, 12-month support.

Out of Scope: Pharmacy integration, AI diagnostics, insurance billing, hardware procurement.

## 4. Project Organisation

| Role | Name | Responsibilities |
| --- | --- | --- |
| Project Sponsor | Dr. Rajiv Patel | Strategic decisions, budget approval, risk escalation |
| Project Manager (Client) | Sarah Chen | Requirements, UAT, stakeholder alignment |
| Project Manager (Vendor) | Priya Sharma | Delivery, team management, status reporting |
| Technical Lead (Vendor) | Amir Hosseini | Architecture, code quality, technical decisions |
| QA Lead (Vendor) | Mei Tanaka | Test strategy, UAT coordination |
| Security Lead (Vendor) | James Okafor | Security architecture, pen test management |
| Product Owner (Client) | Lisa Tanaka | Sprint priorities, feature acceptance |

## 5. Budget Summary

| Total Contract Value | USD $1,850,000 |
| --- | --- |
| Contingency Reserve | USD $92,500 (5%) — held by MediConnect |
| Change Order Budget | To be approved by Project Sponsor on case-by-case basis |
| Invoicing | Milestone-based per SOW-MC-2026-001 Section 6 |

## 6. Key Risks

| ID | Level | Risk | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R-01 | High | Athena Health API v2 credentials delayed | Block Phase 2 integration | Obtain credentials by Week 5; workaround: stub interface |
| R-02 | High | HIPAA pen test uncovers critical findings | Delay go-live | Weekly security reviews; automated SAST in CI from Week 8 |
| R-03 | Medium | Key vendor staff turnover | Knowledge loss, delays | Pair-programming; comprehensive documentation |
| R-04 | Medium | Legacy data quality issues in migration | Corrupted/incomplete records | Dry-run migrations in Weeks 26 and 28; validation scripts |
| R-05 | Medium | Telehealth HIPAA BAA with Twilio delayed | Cannot launch telehealth | Initiate BAA process by Week 4 |
| R-06 | Low | Patient portal adoption below target | No-show goal not met | Onboarding tutorial; clinic champion program |

## 7. Success Criteria

No-show rate <=10% within 6 months of launch.

Provider admin overhead reduced by >=40%.

Zero critical or high security findings unresolved at go-live.

Patient portal SUS score >=80.

System availability >=99.9% over first 3 months of operation.

## 8. Charter Approval

| Project Sponsor | Dr. Rajiv Patel, CTO |
| --- | --- |
| Signature | __________________________ |
| Date | __________________________ |
| Project Manager | Sarah Chen, VP Engineering |
| Signature | __________________________ |
| Date | __________________________ |