# STATEMENT OF WORK

## CareFlow — Patient & Telehealth Management Platform

| Client | MediConnect Health Systems |
| --- | --- |
| Vendor | Stackular Technologies |
| Document ID | SOW-MC-2026-001 |
| Version | 1.4 |
| Effective Date | June 10, 2026 |
| Expiry Date | June 9, 2027 |
| Contract Value | USD $1,850,000 |
| Prepared By | Sarah Chen, VP Engineering — MediConnect |
| Approved By | Dr. Rajiv Patel, CTO — MediConnect |

## 1. Background & Purpose

MediConnect Health Systems operates a network of 47 outpatient clinics across the Pacific Northwest. The organisation currently manages patient scheduling, clinical documentation, and provider communications across three disconnected legacy systems (Athena Health v14, an in-house PHP scheduling portal, and a Microsoft Teams-based telehealth workaround). The resulting fragmentation causes an estimated 3.2 hours of administrative overhead per provider per day, appointment no-show rates of 22%, and recurring HIPAA audit findings related to unsecured messaging.

The CareFlow platform will consolidate all patient-facing and provider-facing workflows into a single HIPAA-compliant, cloud-native SaaS application. This SOW defines the scope of work Stackular Technologies will deliver under Contract MC-2026-TECH-04.

## 2. Objectives

Reduce per-provider administrative overhead by ≥40% within 6 months of go-live.

Reduce appointment no-show rate from 22% to ≤10% via automated SMS/email reminders.

Achieve HIPAA compliance and pass third-party audit within 90 days of go-live.

Eliminate reliance on Microsoft Teams for clinical communications.

Provide real-time patient vitals dashboard for providers during telehealth sessions.

Enable integration with existing EHR (Athena Health API v2) within Phase 2.

## 3. Scope of Work

### 3.1 In Scope

Patient web portal (appointment booking, medical history, secure messaging)

Provider dashboard (schedule management, patient queue, telehealth launcher)

Telehealth video module (WebRTC-based, HIPAA BAA with Twilio)

Automated appointment reminder engine (SMS via Twilio, email via SendGrid)

Role-based access control (Patient, Provider, Admin, Billing, Compliance Officer)

Audit log and compliance reporting module

RESTful API layer for third-party EHR integration

Admin portal (user management, clinic configuration, analytics dashboard)

Mobile applications: iOS and Android (React Native)

Data migration from legacy scheduling system (CSV/API extract)

Staff training (16 hours live + video library)

12-month post-launch support SLA (99.9% uptime guarantee)

### 3.2 Out of Scope

Integration with pharmacy systems (deferred to Phase 3)

AI diagnostic assistance tools

Medical billing / insurance claims processing

Hardware procurement (tablets, kiosk devices)

Legacy Athena Health data migration (client-managed)

## 4. Deliverables

| Deliverable | Description | Due Date | Acceptance Criteria |
| --- | --- | --- | --- |
| D1 — Discovery Report | Documented AS-IS process map and gap analysis | Week 3 | Signed off by CTO |
| D2 — System Architecture | Cloud architecture diagram, tech stack decision, security model | Week 6 | Architecture review board approval |
| D3 — Alpha Release | Core scheduling + provider dashboard functional | Week 16 | UAT pass rate >= 90% |
| D4 — Beta Release | All in-scope modules complete, telehealth live | Week 24 | UAT pass rate >= 95%, zero P1 bugs |
| D5 — Security Audit | Third-party HIPAA penetration test report | Week 26 | No critical findings unresolved |
| D6 — Production Launch | Full go-live with data migration complete | Week 30 | Uptime >= 99.9% over 7-day burn-in |
| D7 — Training Completion | All staff trained, documentation delivered | Week 31 | Training sign-off sheets |
| D8 — Handover Package | Source code, infra-as-code, runbooks, API docs | Week 32 | Vendor sign-off |

## 5. Timeline & Milestones

Total project duration: 32 weeks (June 10, 2026 — January 29, 2027)

| Phase | Duration | Key Activities |
| --- | --- | --- |
| Phase 0 — Discovery | Weeks 1-4 | Stakeholder interviews, AS-IS mapping, requirements sign-off |
| Phase 1 — Architecture | Weeks 5-7 | Tech stack finalisation, cloud setup, CI/CD pipeline, security baseline |
| Phase 2 — Core Build | Weeks 8-20 | Patient portal, provider dashboard, scheduling engine, RBAC |
| Phase 3 — Telehealth | Weeks 18-24 | Video module, reminder engine, mobile apps (parallel track) |
| Phase 4 — QA & Security | Weeks 22-27 | Integration testing, penetration test, UAT, bug remediation |
| Phase 5 — Migration | Weeks 26-29 | Data migration dry-run x2, production migration |
| Phase 6 — Launch & Train | Weeks 29-32 | Phased go-live (5 pilot clinics -> all 47), staff training |

## 6. Payment Schedule

| Milestone | Amount (USD) | Due |
| --- | --- | --- |
| Contract execution | $185,000 | June 10, 2026 |
| D2 — Architecture approved | $277,500 | July 22, 2026 |
| D3 — Alpha UAT passed | $370,000 | October 7, 2026 |
| D4 — Beta UAT passed | $370,000 | November 25, 2026 |
| D6 — Production launch | $462,500 | January 8, 2027 |
| D8 — Handover complete | $185,000 | January 29, 2027 |

Total: USD $1,850,000 (exclusive of applicable taxes)

## 7. Assumptions & Dependencies

MediConnect will provide a dedicated Product Owner (min. 0.5 FTE) for the project duration.

Athena Health API v2 credentials and sandbox access provided by Week 5.

MediConnect IT will provision VPN access for Stackular engineers by Week 2.

HIPAA Business Associate Agreement (BAA) executed with Twilio and AWS before Week 8.

Legacy scheduling data export (CSV) delivered by MediConnect by Week 25.

MediConnect security team available for architecture review in Weeks 5-6.

## 8. Acceptance Criteria

Each deliverable is accepted when: (a) all documented test cases pass at the stated pass rate threshold, (b) no Priority 1 or Priority 2 defects remain open, (c) the MediConnect Product Owner signs the Acceptance Certificate within 5 business days of delivery. Silence beyond 5 business days constitutes deemed acceptance.

## 9. Change Management

Any change to scope, timeline, or cost requires a signed Change Order (CO) before work begins. Changes requested within 72 hours of a milestone do not extend the milestone date unless the CO explicitly states otherwise. Stackular will provide a CO impact assessment within 3 business days of a change request.

## 10. Warranties & SLAs

12-month post-launch warranty covering defect remediation at no charge for P1/P2 bugs. Production SLA: 99.9% monthly uptime (<=43.8 min downtime/month). RTO: 4 hours. RPO: 1 hour. Excluding scheduled maintenance windows (max 4 hours/month, 48 hours notice).

## 11. Confidentiality & IP

All work product, source code, and documentation produced under this SOW is the sole property of MediConnect Health Systems upon full payment. Stackular retains rights to generic, non-client-specific frameworks and tooling. Both parties are bound by the NDA executed February 14, 2026 (NDA-MC-2026-003).

## 12. Signatures

| MediConnect — Authorised Signatory | Dr. Rajiv Patel, CTO |
| --- | --- |
| Signature | ___________________________ |
| Date | ___________________________ |
| Stackular Technologies — Authorised Signatory | Amir Hosseini, CEO |
| Signature | ___________________________ |
| Date | ___________________________ |